## Sheet1
ID | Date | Description | probability | Effect | Ranking
1 | 2017-10-10 | Communication breakdown between group members | 10 | 5 | 50
2 | 2017-10-10 | Unforeseen problems with architectural choices | 6 | 8 | 48
3 | 2017-10-10 | Constant changing requirements lead to little progress | 5 | 7 | 35
4 | 2017-10-10 | Gameplay breaks down or fails to work as intended | 8 | 8 | 64
5 | 2017-10-10 | Problems with both clients operating simultaneously | 8 | 8 | 64
6 | 2017-10-10 | Loss of motivation to work together on the project | 10 | 6 | 60
7 | 2017-10-10 | Distraction during work | 10 | 4 | 40
8 | 2017-10-10 | Lack of resources (money, sleep, food) | 4 | 9 | 36
9 | 2017-10-10 | Lack of knowledge or skill (inexperienced group members) | 8 | 9 | 72
10 | 2017-10-10 | Serious debugging or refactoring needed later in project | 8 | 7 | 56
11 | 2017-10-10 | Network failure between databse / Web services | 4 | 8 | 32
12 | 2017-10-10 | Group members failing to show up for work | 4 | 5 | 20
13 | 2017-10-10 | Size of the group causing work issue | 3 | 7 | 21
14 |  |  |  |  | 0
15 |  |  |  |  | 0
16 |  |  |  |  | 0
17 |  |  |  |  | 0
18 |  |  |  |  | 0
19 |  |  |  |  | 0
20 |  |  |  |  | 0
21 |  |  |  |  | 0
22 |  |  |  |  | 0
23 |  |  |  |  | 0
24 |  |  |  |  | 0
25 |  |  |  |  | 0
26 |  |  |  |  | 0
27 |  |  |  |  | 0
28 |  |  |  |  | 0
29 |  |  |  |  | 0